Educational Assistant/Paraprofessional OAR Revision Timeline

January 19, 2010

| Date | Activity |
| --- | --- |
| November 20, 2009 | Stakeholder meeting |
| January 15, 2009 | Post Survey |
| February 3, 2010 | Survey Information due |
| February ?, 2010 (TBD) | 2nd Stakeholder Webinar Send items to group electronically (Refine draft based on comments) |
| February 3, 2010 | Send Cindy rule draft for filing |
| February 15, 2010 | Filing deadline for March 24 rule hearing – Rule posted on state board web site and sent to ODE stakeholders |
| February 19, 2010 | Notify public of posting of draft revisions |
| February 22, 2010 | Post Draft Revisions for 30 d. public comment/notice 60 d prior to adoption |
| March 24, 2010 | Rule Hearing & Comments due on rule draft |
| April 5, 2010 | Topics due to Michelle Hooper for SB Agenda |
| April 12, 2010 | Documents due to Michelle Hooper for SB Agenda |
| April 22, 2010 | SBE 1st Read |
| May 3, 2010 | Topics due to Michelle Hooper for SB Agenda |
| May 10, 2010 | Documents due to Michelle Hooper for SB Agenda |
| May 20, 2010 | Adoption by State Board To include guidance that will help districts as they implement the revised OARs |