Oregon Address Point Framework Data Funding Request

Background:

Address information is the basis of many (if not most) governmental transactions and services. In most cases, citizens must provide a viable address in order to qualify for services, and governments use those addresses in a myriad of ways – to provide emergency response, to allocate human services and education services, to request payment for government-run utilities, and for planning activities. Portraying address locations accurately and consistently in relation to other features on a map is essential to the efficient provision of governmental services.

Government addressing authorities use many unique processes to generate, maintain, use, and retire addresses. In order to properly draw and locate an address on a digital map, two methods are widely used:

- Dynamic generation of address point features using an address parsing process followed by comparison with a centerline road layer that has address range attributes assigned to the centerline, and

- The creation and storage of static address point features relating a structure to specific locational coordinates (e.g., latitude and longitude), which are then address-matched with the address provided.

Both of these methods have advantages and disadvantages, and both have investment and maintenance costs related to addresses and the comparison of data layers. Moreover, both have assumptions (either explicit or implicit) built into their workflow processes that affect the positional accuracy of the mapped point features.

Currently, each jurisdiction handles address information in its own way. There are many different address datasets, with different levels of data quality (accuracy, completeness, and timestamps).  These datasets are kept in many different parts of government at all jurisdictional levels. Some maintain their own data, while others rely on regional governments or commercial entities for that work. The longer-term goal of this GEO proposal is to create a centralized, up-to-date, standards-based, easily available repository of the most accurate seamless statewide dataset representing discrete address points for addressable structures (residential and non-residential). We believe that this type of database repository will satisfy most (if not all) end-users’ business needs for address information.  Typical business needs include emergency response, citizen and business mailings, urban and regional planning, redistricting, candidate location verification, etc.

A centralized, web-accessible database of address point locations, -one that is built incrementally and maintained at the most-local level that is possible and feasible-, will decrease the effort and expense required to interact with Oregon citizens and businesses using their addresses. We have an opportunity now to leverage the federal investment in addressing and broadband internet service access as represented by data layers that have been purchased on our behalf. However, the data layers themselves quickly decrease in value if we do not create a maintenance process for the address point features. DAS GEO is proposing a means to do that in seven integrated activities. We believe that all of the resources needed to maintain the address point database are already available for that task. In fact, it is being done (redundantly, we believe) at all levels of government in the state. Adopting an address point standard, creating a statewide address point repository, and developing the maintenance processes to keep it relevant, are needed, timely, and economical.

For the purposes of this development project, we intend to use the emergency response business process as the primary driver.  Emergency response requires the highest level of accuracy and completeness for address data of any business process.  We believe if we can meet the needs of the emergency response community for address points, we will have developed a database that can easily meet other business needs.

The following activities create a path toward that vision.  While they are described as discrete activities, they are integrated components of a complete process and most will actually proceed in parallel. They will require fully dedicated internal and external resources, as noted in the cost breakdowns. Internal resources include technical and administrative staff, which will be redirected from existing projects, representing an additional opportunity cost.  External resources will be contracted, as needed.  This will be the most expedient and cost effective means for meeting the described deadlines.

Activity # 1: Develop environment for hosting Address Point Database

The Address Points Database (APD) is a SQL Server relational database containing address attributes linked to a GIS feature class containing the geographic locations of address points.  This authoritative address data will be maintained in a secure environment with the SDC standard database backup services to ensure restore capability and prevent data loss.

Detailed Project Narrative:

This activity involves deploying the APD on GEO-administered servers at the Oregon State Data Center (SDC). It is essential that the system architecture (database, software and

hardware) employ a mature disaster recovery model to ensure maximum uptime.

SDC not only provides database backups, but also backup imaging of server system configuration, allowing for quick recovery of a server and all its applications in the event of a server failure. The APD should incorporate a staging environment that will accept user contributed data, and a production environment which has gone through various QA/QC checks. In order to enable viewing/editing capabilities over the web, access to the ADP will be made available thorough GEO's production server environment. User-level security will be enabled to restrict editing to authorized users only.

Business Purposes Served

- Maximum uptime of APD by deploying on stable and robust system architecture

- Ensure that APD can be restored in case of system failure by routine backups

- Enable editing environment over the web

- By implementing user-level security, only authorized users will be able to view/edit data

Deliverables:

- Server environment built, with database access enabled

- Address Point Database deployed (with data from four pilot counties)

- System environment documentation

- Procedures and schedule for APD backup

- Define procedure for maintaining database of users for security

Timeframe: March, 2012 – May 2012

Preliminary task breakdown for Activity #1:

- Document existing database backup and recovery models for use with APD

- Document existing system architecture for use with APD

- Develop and document staging environment and production environment for APD

- Procedures and schedule for APD backup

- Define procedure of QA/QC checks for APD

Resources required: System Architecture

Cost estimate: 150 internal resource hours at $40/hr = $6,000

Activity #2: Develop a comprehensive database of address management operations in Oregon

The long-term vision for an Address Points Database (APD) involves participation from all address authorities across the State of Oregon. By documenting the jurisdictions and personnel associated with address assignment processes, we will identify the primary stewards and stakeholders for the APD.

Detailed Project Narrative:

The immediate goal of this activity is to create a database of the organizations and people that are responsible for assigning addresses to structures in Oregon. The secondary goal of this activity is to determine who will fill the role of contributor in each local jurisdiction. This role may be filled by the city/county, the PSAP, or through an outside agency based upon an established stewardship agreement.

Business Purposes Served

- Establish addressing maintenance procedure in local areas where that process is ad hoc

- Alignment of processes with addressing standards at local levels as opportunities arise

Deliverables:

- Summary of statutory authority for address creation;

- Database of address management authorities;

- Maintenance mechanism for authoritative contacts related to each jurisdiction.

Timeframe: Duration of project (Sept, 2011 – Sept, 2012)

Preliminary task breakdown for Activity #2:

- Research statutory authority for address creation/assignment

- Contact local addressing authorities to document activity

- Refine list/database of contact information as needed

- Establish contributor role within each jurisdiction

- Document hierarchy of addressing authority, collator, and contributor roles for each jurisdiction

Resources required: Coordination, Data Administration, OEM data source(s) and agreements

Cost estimate: 250 internal resource hours at $40/hr = $10,000

Activity #3: Develop and describe methodology to import existing spatially referenced address point data into Oregon’s address point data model

Activity #3 involves:

- developing the method(s) that support the import of existing address point data from individual sources into the Address Point Database (APD);

- creating a date and time stamp and a unique identifier field (UUID) for each imported point record;

- creating a contributor identifier field for each imported point record;

- storing those new attributes along with the address point record; and then

- verifying the address point can be exported in a standardized format which meets the business needs for OEM.

Detailed Project Narrative:

The Oregon Address Points Data Model was developed using federal funds in support of the Statewide Broadband Mapping Initiative. It is based on the recently adopted FGDC Address Data Standard, and contains recent data compiled for four rural Oregon counties. The immediate goal of Activity #3 is to define and document the APD transaction process using sample data supplied by Oregon Emergency Management (OEM).  The steps involved include: import data from a contributor with a specific business process, define how to attach the timestamp, UUID, and contributor information to the imported data, describe the process to crosswalk the existing data into the database, and describe the process to retrieve that same data, demonstrating that no data loss or corruption took place.  This documentation – essentially an APD use case - can then be modified for each contributor so that each data intake action will be defined based on the contributor’s individual business need.  Portions of this activity will be contracted to external resources.

Business Purposes Served

- Multiple point features can be stored for each address location, as required by the data contributor’s business process(es).  Multiple points will be differentiated by the addressing authority using pre-determined location identifier fields.

- Address point data for surrounding jurisdictions can be made available to users for mapping and analysis outside a contributor’s jurisdictional area

- DAS/GEO, as the APD steward, will manage the database and serve the address point data back to consumers (contributors, stakeholders, public – as appropriate)

Deliverables:

- Address point data import use case describing specific processes

- Populate Address Point Database (using sample data from a single new contributor), verifying that all data entered into database can be accessed and extracted

- Ability to readily modify use case as a proof of concept for additional (one or more) contributors

- Delivery of scripts (e.g. SQL scripts) used in the address point data import/export process

Timeframe:  Apr, 2012 through Jun, 2012

Preliminary task breakdown for Activity #3:

- Statement of Work for external work

- Preparation and submittal of RFP for external resource

- Coordination of use case development between OEM and DAS/GEO

- Creation of import/export process/methodology, based on requirements defined by use case

- Creation of UUID, timestamp, and contributor attributes for each address point record

- Appropriate population of “new” attribute fields in APD

- Quality testing of data stored in and retrieved from APD

Resources required:  Coordination, Data Administration, OEM data source, Current Address Point Database, Development environment, Testing environment

Cost estimate: 100 internal resource hours at $40/hr = $4,000; and 60 external resource hours at $150/hr = $9,000, totaling $13,000

Activity #4: Develop methodology to incorporate edits from address managers into existing, standard-based address point database

Activity #4 expands the scope of Activity #3 to include editing existing address point data stored in the APD.  It will develop a process to:

- Replace address point data in the database with updated information and locations, and

- Add new address point locations (such as multiple point locations/features for an existing address or new address point locations associated with newly assigned addresses) to the existing address point database to satisfy the business requirements of various contributors.  Change management and tracking will be defined and tested.

Detailed Project Narrative:

The Address Point Database (APD) is a dynamic storage solution for statewide address points.  Since we expect that business requirements will vary by contributor, flexibility in data storage and retrieval mechanisms is of paramount importance.  This second activity will define, build, and test this flexibility by incorporating differing address point datasets, including datasets that have multiple point locations associated with one street address. We will design functionality to test the ability to retrieve the correct point feature for a given street address based on the contributor’s business process need (for example, returning a driveway location when querying the database for vehicle routing, as opposed to the building rooftop location, which may be more important for a different business process).  We will discuss with contributors to establish update procedures and schedules.  Portions of this activity will be contracted to external resources.

Business Purposes Served (in addition to business purposes from Activity #3):

- Contributors will submit address point data edits (changed or new address points), and as the steward of the APD, DAS/GEO will update the database and serve the data back to consumers based on documented procedures and schedules

- Change management and tracking schema will be defined and tested

Deliverables:

- Data import use case describing specific editing/updating processes associated with new address point feature data

- Populate database with sample data, which includes multiple points for the same address, as well as replacement data for a given area (simulating updated data from an existing contributor). These processes will be tested for validation/verification

- Change management schema and storage documentation

- Retrieve appropriate data for given contributor

Timeframe:  May, 2012 through Aug, 2012

Preliminary task breakdown for Activity #4:

- Statement of Work for external work

- Preparation and submittal of RFP for external resource

- Coordination of use case development between OEM and DAS/GEO

- Locating an existing address point dataset to import that satisfies use case input requirements

- Creation of import/replace/export process/methodology based on requirements defined by use case

- Creation and verification of UUID and timestamp attributes for each new address point record

- Quality testing of data stored and retrieved

- Publishing test results

Resources required:  Coordination, Data Administration, OEM data source, Development environment, Testing environment, and Production environment

Cost estimate: 100 internal resource hours at $40/hr = $4,000; and 240 external resource hours at $150/hr = $36,000, totaling $38,000

Activity #5: Design/develop methodology to convert existing non-GIS address management practices into APD data compilation process

Activity #5 creates a process through which local governments can create address point data where none exists.  This activity will leverage the lessons learned during the creation of four counties’ address point data to satisfy local business requirements, while creating an address point feature set that conforms to the APD data environment.  Change management and tracking for the APD will be defined, documented, and tested.

Detailed Project Narrative:

For addressing authorities that do not currently manage addresses in a GIS format, we plan to define, build, and test the processes by which the address point business requirements of a local government might be met. I In collaboration with them, we willcreate address point data for their benefit and for the APD.  To do so, we will work with local address authorities to understand their needs and create suggested processes for development of address point data, data maintenance procedures, and workflow schedules.  Portions of this activity will be contracted to external resources.

Business Purposes Served:

- Local government needs related to address point development and maintenance will be documented

- Address point data will be created where none currently exists, and incorporated into the APD

- Address point data for surrounding jurisdictions can be made available to users for mapping and analysis outside a contributor’s jurisdictional area

- Address point data that are created under this activity will be provided to DAS/GEO, the steward of the APD. DAS/GEO will create timestamp and UUID in the database and serve the address point data to consumers (contributors, stakeholders, public – as appropriate)

Deliverables:

- Address point data creation use case documentation that describes the specific address development processes for each addressing authority

- Populate address point database with any and all address data that is created

- Change management schema and storage documentation

Timeframe:  Jul, 2012 – Dec, 2012

Preliminary task breakdown for Activity #5:

- Statement of Work for external work

- Preparation and submittal of RFP for external resource

- Meet with Local Government addressing authority to determine business need for address point data and ability/willingness to collaborate

- Coordination of use case development between DAS/GEO and each local government addressing collaborator

- Create address point dataset that satisfies use case input requirements

- Creation of import/replace/export methodology based on requirements defined by use case

- Creation and verification of UUID and timestamp attributes for each new address point record

- Quality testing of data stored and retrieved

- Publishing test results

Resources required:  Coordination, Data Administration, OEM data source, Development environment, Testing environment, and Production environment

Cost estimate: 300 internal resource hours at $40/hr = $12,000 and 80 external resource hours at $150/hr = $12,000, totaling $24,000

Activity #6: Develop and deploy address point data stewardship agreements

Activity #6 consolidates and memorializes the processes at the state and local levels relating to maintaining and updating the APD.  Since this phase relies on the successes of the first several activities, it is an intrinsic part of them all. Activity #6 documents the process for each addressing authority to:

- contribute their data to the APD (in either tabular or GIS format);

- update the address point data stored in the APD;

- retrieve the address point data as needed;

- store address point data locally and within the APD; and

- distribute address point data back to consumers (contributors, stakeholders, public – as appropriate).

We will document the process(es) used to replace current address point data in the production environment, as well as store replaced address point data for retrieval and quality control.  Change management and tracking will be defined and tested.  Data stewardship procedures and agreements will be defined, documented, and implemented.

Detailed Project Narrative:

A use case will be created to describe the address point maintenance procedure for each contributor/participant/addressing authority.  This use case will describe the following processes: uploading modified data to the APD, replacing current data in the production environment, archiving historical data, and retrieving historical data. Data stewardship procedures and agreements will be defined, documented, and implemented.

Business Purposes Served:

- Data stewardship roles will be defined

- Contributors will submit updated data, and as the steward of the APD, DAS/GEO will update the database and serve the data back to consumers based on established procedures and schedules

- Contributors will be responsible for retrieval and distribution of data as needed to agencies within their local jurisdiction.

- Data archiving and retrieval procedures will be defined

- Change management and tracking schema will be defined and tested

- The data within the database will also be made available to state agencies and via web services to the public

Deliverables:

- Data storage and retrieval use case describing specific processes

- Populate database with replacement data which will be tested for data corruption as proof of use case

- Archive historic data and retrieve same

- Change management schema and storage documentation

- Retrieve appropriate data for given contributor

- Established schedule for contributor’s ongoing address point data updates

Timeframe:  Sept, 2011 through Dec, 2012

Preliminary task breakdown for Activity #6:

- Coordination of use case development

- Importing dataset to import which satisfies use case input requirements

- Writing script for import/replace/export based on requirements defined by use case

- Archiving historic address point data

- Verifying UUID

- Quality testing of data stored and retrieved

- Publishing test results

- Coordination and management of data updates

Resources required:  Coordination, Data Administration, OEM data source, Development environment, Testing environment, and Production environment

Cost estimate: 600 internal resource hours at $40/hr = $24,000

Activity #7: Develop methodology to allow efficient low-overhead editing capabilities for contributors, as well as cost effective method for delivery of address point data to end users

Activity #7 is an integral part of all the above activities, and represents the development of the “front end” methodology for the import and export of address point data from the APD. The primary tasks of this activity include:

- Developing a beta version of “viewer” so that authorized end users can examine, select, download, and submit changes to address point data that is stored in the APD

- Documenting best practices and authorization for appropriate end users to view, download, and/or submit changes

- Creating web services, including feature and geocoding services, based on APD

Detailed Project Narrative:

In order to obtain end user support for this project, it is imperative to create a seamless and efficient process for accessing, viewing, retrieving, and editing address point data.  Ideally, the appropriate solution will have a small overhead in direct or indirect costs to the end user, including training, storage, or application/processing overhead.  To accomplish these goals, a web-based address point data viewer based on the APD, will be built and documented. The application will be secured so that only authorized end users will have access to certain functionality, based on pre-arranged and documented standards for address point data contributors.

In addition to the web viewer/editor, address point data will also be exposed to users through two REST-based GIS web services:

- Dynamic feature service that will return the points and selected attribute data for select area or matching a specific query

- Geocoding service, capable of returning the latitude and longitude of a given address (or, alternately, the address for a given latitude/longitude)

Business Purposes Served:

- Contributors will have a methodology to submit address point data edits (changed or new address points), incurring only minimal additional costs associated with data storage, training, or computer processing requirements

- Access (viewing, retrieving, and editing) to the address point data will be controlled as per agreement with each contributor, but government agencies will have access to the data

Deliverables:

- Web-based application that allows viewing, submitting edits, and downloading address point data from the APD as applicable

- Documented methodology for using submitted changes to update APD

- Change management schema and storage documentation

- Documented authorization for each contributor describing allowed access to address point data stored in the APD

- Geocoding and dynamic feature web services for exposing address point data via REST interface

Timeframe:  Mar, 2012 through Dec, 2012

Preliminary task breakdown for Activity #7:

- Statement of Work for external work

- Preparation and submittal of RFP for external resource

- Coordination of use case development

- Modifying existing web-based viewer to allow security protocols

- Creation of import/replace/export process/methodology based on requirements defined by use case

- Establishing authorization criteria based on individual contributors and general end users as applicable

- Quality testing of data stored and retrieved

- Publishing test results

- Publishing documentation for usage of web-based tool

- Developing process for updating address locator (geocoder) with data from APD

- Documenting address web services

Resources required:  Coordination, Data Administration, Development environment, Testing environment, and Production environment

Cost estimate: 175 internal resource hours at $40/hr = $7,000 and 120 external resource hours at $150/hr = $18,000, totaling $25,000

Total Amount Requested:  $140,000

Contact Information:

Project Coordination

David Snader

Local Government GIS Coordinator

Department of Administrative Services, Geospatial Enterprise Office.

20370 Saghali Ct.

Bend, OR  97702

(503) 798-0201, david.snader@das.state.or.us

External Resources

To be contracted as per Oregon procurement processes

Internal Resources

Data Administration – Dave Mather

Web Design and Implementation – Erik Endrulat

Legal and Administrative – Cy Smith, Milt Hill, Dave Snader