| OREGON PUBLIC HEALTH DIVISION Health Promotion & Chronic Disease Prevention Section |  |
| --- | --- |

800 NE Oregon St, Ste 730 Portland, OR 97232 Voice (971) 673-0984 Fax: (971) 673-0994 TTY (971) 673-0372

M E M O

Date:	December 30, 2011

To:	County and Tribal Tobacco Prevention Program Coordinators

County Healthy Communities Implementation Program Coordinators

From:	Healthy Communities/TPEP Community Program Liaisons

Re:	QUARTERLY AND SIX-MONTH REPORT REQUEST

Due:	January 20, 2012

All submitted reports should include a Quarterly Progress Report and a 6-Month Narrative Report.

Six-Month Narrative Report Instructions (July 1, 2011 through December 31, 2011)

Please write a 1-2 page cover letter describing highlights from the last six months, using the following questions as a guide:

- Describe the key successes or outcomes over the last six months as you have made progress on your workplan objectives.

- Describe any new ‘champions,’ stakeholders, or partnerships that are developing as a result of your efforts.

- Describe any barriers or challenges to working on each of your objectives, and how you addressed them (lessons learned).

- Describe next steps for your objectives.

- Describe any questions, concerns, technical assistance needs, or resources that you need from OHA/HPCDP.

Quarterly Progress Report Instructions (October 1, 2011 through December 31, 2011)

Report your progress toward completing planned activities during the quarter. The report may be formatted in either narrative or table format, following these guidelines:

- Make your notes on the workplan itself, under or next to each activity. See the format example below.

  - If you are using a workplan format that includes a column for quarterly reporting, put your progress notes there.

- There should be notes for every planned activity for the quarter in the workplan, whether or not they took place exactly as planned.

- Your progress notes should include:

- The quarter you are reporting on

- For activities that were conducted as planned, simply provide the actual Start and End dates for each activity for the quarter

- For activities that were not conducted as planned, describe why and how the activities were conducted differently, including any changes in your Start and End dates

Please clearly mark all forms with the county name and report date.

Optional: Feel free to include any additional information, such as media clips or pictures of events.

Quarterly Report Format Example:

- Coordination and Collaboration

We will continue our work with the Superintendent and Administrative Assistant at the school district. As necessary, we will bring in more partners from the community, staff and/or students to add to this workgroup to make recommendations to the School Board. Planned Start/End Dates: September 2011 – December 2011.

First Quarter Progress: Actual Start Date was September 2011. Actual End Date: N/A. This activity will continue through December 2011.

Second Quarter Progress: Actual End Date: N/A. Workgroup has been formed and two meetings were held during the quarter; this activity will continue through January 2011 to allow more time for the workgroup to finish preparing recommendations for the Board.

Email or mail the entire report to your Community Programs Liaison:

Sabrina Freewynn 	sabrina.l.freewynn@state.or.us

Tara Gedman		tara.e.gedman@state.or.us

Jacqueline Villnave	jacqueline.m.villnave@state.or.us

April Rautio 		april.l.rautio@state.or.us

Tia Skerbeck		christia.d.skerbeck@state.or.us

Rebecca Pawlak	rebecca.l.pawlak@state.or.us

Thank you for all your efforts for healthy communities throughout Oregon!