## Sheet1
2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01
VISTA #1-Divneet | [11 empty] | VISTA #2-Mikkel | [11 empty] | VISTA # 3
Last updated: |  | 2011-11-29 | [9 empty] | Health Status Report Update 2011-12
Public Health Annual Plans
[13 empty] | TR-Planning-JS/CF | TR-Doc Collection-JS et al. |  | TR-Doc Org-JS/CF | TR-Site Visit
[11 empty] | CCO- Gov. Appt. Work Group Discussions |  |  |  | 12/5-Measure due to Legislature |  | ~2/1-3/6: Legislative Session
FQHC Community Health Assessment
Samaritan Community Health Status Assesment(s)-due in 2012
Strategic Initiative #1-Team Vacinne
BCHS Integrated Strategic Plan
Public Health Accreditation Preparation
[14 empty] | Statement of Intent Planning | Online Orientation Completion-AB/MA | SOI-Submission-MQ/AB | SOI-acceptence-PHAB | Access to Online Application 12 months if SOI submitted and accepted in 2011-2012
[14 empty] | CHA-Planning-PP/AB/TD/SG | Community Health Assessment-PP |  |  |  | CHA-Drafting | CHA-Finializing/Formatting
[15 empty] | CHIP-Planning-PP/AB/TD/SG | Community Health Improvement Plan-Patty |  |  |  | CHIP-Drafting | CHIP-Finializing/Formatting
[16 empty] | DSP-Planning-CF/AB/MA/SD | Departmental Strategic Plan-AB/CF |  |  |  | DSP-Drafting | DSP-Finializing/Formatting
[22 empty] | Application Planning-MQ/AB | Application-Submission with Fees and Pre-Reqs-MQ/AB | Application-acceptence/completeness check-PHAB | In Person Accreditation Coordinator Training-AB | Access to Online Documentation uploading 12 months once link has been issued to HD)-???
Quality Improvement Plan and Implementation
Gap Analysis and implementation of procedures to fill gaps
PHA-BETA Documentation Collection and Content Review | [11 empty] | PHA Documentation Planning and Crosswalking-MQ
PHA Documentation Collection and Content Review-MQ et al.
PHA Detail Review/Revision-MQ/AB et al.
PHA Expert (PHABULOUS) Review-PHA Team
PHA Doc Annotation-Finializing/Formatting-MQ/PHA Team
E-PHAB Documentation Submission-MQ/AB/??
[26 empty] | PHAB reviews documentation for completeness and accepts documentation | PHAB select Site Visit Team/HD reviews for conflicts of interest | Site Visit is Scheduled-PHAB/AB | Site Visit Team reviews all documentation | Site Visit Team conducts site visit
[30 empty] | Site Visit Team submits Report to PHAB | HD Review report for factual accuracy | Accreditation Committee Review | Determination of Accreditation statues | PHAB notifies HD of PHA status