|  | Related to PREVIOUS YEAR (2020-2021 grants) | Related to CURRENT YEAR (2021-2022 grants) | Related to NEXT YEAR (2022-2023 grants) | OTHER |
| --- | --- | --- | --- | --- |
| JULY | - Monitor remaining grant reimbursements - Monthly spending status meeting - Remind grantees to submit final reports - Begin entering SPR data | - Prepare/send updated SWLP info to SWLP project managers - Schedule quarterly check-in meetings with SWLP project managers - Enter FFATA info into fsrs.gov | - Prepare draft of Annual Program Plan - Update Advisory Committee notebook - Host Advisory Committee meeting, orient new members, approve Annual Program |  |
| AUG | - Monitor remaining grant reimbursements - Monthly spending status meeting - Remind grantees to submit final reports - Continue entering SPR data | - Monitor status of returned agreements - Complete Risk Assessments of new grants (Assistant provides draft) | - Revise Gen Info/Guidelines; EZ, LOI/Project, Special Proj, Multi-year, and SWLP guidelines and applications - Ask NC Cardinal for guideline, application updates - Prepare info for web page updates - Prepare announcement for all new program info |  |
| SEPT | - Monitor remaining grant reimbursements - Monthly spending status meeting - Remind grantees to submit final reports - Request final SWLP figures from Budget Officer - Send SWLP project managers info about submitting final report(s) - Prepare announcement for public view of SPR - Create link on web page for public view of SPR | - Send reminder to grantees of non- returned agreements | - Post new program info to website - Webinars/workshops for potential LOI or grant applicants | - Participate in Five-Year Plan Evaluation, as needed |
| OCT | - Remind any remaining project managers to submit final reports - Invite SWLP project managers to submit final report(s) - Continue entering SPR data | - Schedule Jan. monitoring visits - Prepare RFA/travel request for Jan. monitoring visits - Quarterly check in w/SWLP project managers | - Webinars/workshops for potential LOI or grant applicants | - Participate in Five-Year Plan Evaluation, as needed |
| NOV | - Continue entering SPR data - Consider funds transfer (internal) to avoid de-obligating federal $$ |  | - Receive all LOIs (Program Asst. logs in, cursory review for major data like signatures, agreement of top page with budget totals, etc.) - Coordinate Advisory Committee conference call to review LOIs, share documents, etc. - Prepare review assignments, memo, share LOIs with LD Consultants, schedule review day/times - Conduct staff grant review of applications - Conduct Sr Mgmt grant review of applications, SWLPs |  |
| DEC | - Submit LSTA State Program Report (SPR), due to IMLS on Dec 30 | - Arrange logistics for Jan/Feb monitoring visits of multiyear projects - Send questions/info for multiyear monitoring visits - Complete interim FSR | - Host Advisory Committee conference call to review LOIs - Notify LOI applicants; provide feedback |  |
| JAN |  | - Conduct monitoring visits for multiyear projects; provide feedback - Quarterly check in w/SWLP project managers | - Review & modify grant review forms/criteria as needed |  |
| FEB |  | - Monitor grantees spending status - Contact libraries with no expenditures to date - Monthly spending status meeting | - Receive all grant applications (Program Asst. logs in, cursory review for major data like signatures, agreement of top page with budget totals, etc.) - Prepare review assignments, memo, share applications with LD Consultants, - Prepare schedule details for review days/times | - Review final draft of Five-Year Plan Evaluation |
| MAR | - Make any corrections to SPR (or sooner if IMLS feedback received) | - Prepare IMLS Compliance Supplement for next FY - Monthly spending status meeting |  | - IMLS G2S Conference? - By Mar 30: Five-Year Plan Evaluation due to IMLS |
| APRIL |  | - Prepare email to grantees about current spending status - Monthly spending status meeting - Review/update online Final Report Form - Quarterly check in w/SWLP project managers | - Conduct staff grant review of applications - Conduct Sr Mgmt grant review of applications, SWLPs - Recruit for upcoming Advisory Committee vacancies - Prepare letters for outgoing Advisory Committee members | - Issue RFP for Five-Year Plan Evaluation - LSTA Advisory Committee -- invite nominations from COIs (due in time to consider at May meeting) - Develop new Five-Year Plan - Revisions (if substantive) to Five-Year Plan due to IMLS by April 1 - Consider applying for MOE Waiver |
| MAY |  | - Monitor grantees spending status - Monthly spending status meeting - Prepare email to notify grantees of mid-June federal expenditure cut-off | - Host Advisory Committee meeting, grant reviews - Prepare notifications for all applicants, prior to public announcement in June - Prepare media release for library and DNCR - Review/edit award abstracts for website |  |
| JUNE |  | - Monthly spending status meeting - Prepare updates to reimbursement and budget revision documents - Update Executed Agreement and media release to return with signed grant agreements - Process reimbursements by mid-June federal expenditure cut-off | - Update Advisory Committee Roster - Prepare letters for incoming Advisory Committee members - Prepare announcement of new grant awards, post to website - Prepare agreement letters, agreements, reimbursement and budget revision info, and other documents - Monitor distribution of grant agreements - Update SWLP notebook | - Select consultant/firm for Five-Year Plan Evaluation - By June 30: new Five-Year Plan due to IMLS - By June 30: review Program Assistant work plan - Update LSTA Overview Consultant and Grants Assistant documents |

Other:

Ongoing – reimbursement processing

Ongoing – approval of budget revisions

Ongoing – consultations with current, future applicants

In Fourth Year of Five Year Plan – Do evaluation

In Fourth Year of Five Year Plan, after evaluation – Write new Five Year Plan

Next IMLS Monitoring Visit is