Crossed out text are tasks cancelled due to Covid-19

|  | Related to PREVIOUS YEAR (2020-2021 grants) | Related to CURRENT YEAR (2021-2022 grants) | Related to NEXT YEAR (2022-2023 grants) | OTHER |
| --- | --- | --- | --- | --- |
| JULY | - Process remaining grant reimbursements - Remind grantees to submit final reports - Reconcile award payments and carryforward balance - Begin entering SPR data if ready | - Post updated reimbursement and budget revision documents - Log and return signed grant agreements with Executed Agreement memo - Prepare Reimbursement Pay Sheets, Pay Memos, and individual project spreadsheets - Prepare spreadsheet of FFATA information in consultation with Federal Programs Consultant - Update website with SWLP projects | - Post new Advisory Committee Roster on web page - Update Advisory Committee historical list - Prepare copies of Advisory Committee notebook - Prepare nametags, packets for Advisory Committee meeting; arrange catering - Process Advisory Committee reimbursements | - NCLA agreements (odd years) |
| AUG | - Process remaining grant reimbursements - Remind grantees to complete projects and submit final reports - Continue entering SPR data/begin if ready | - Monitor status of returned agreements - Process reimbursement requests - Monitor incoming Conference Scholarship applications, log - Start processing Risk Assessments for new grants, with Federal Programs Consultant to complete final steps |  |  |
| SEPT | - Process remaining grant reimbursements - Continue entering SPR data | - Monitor status of returned agreements - Process reimbursement requests - Monitor incoming Conference Scholarship applications, log - Agreements for Conference Scholarships | - Post new docs to web page: Gen Info/Guidelines; EZ, LOI/Project, Special Proj, Multi-year, and SWLP guidelines and applications - Post Annual Program Plan announcement | - Participate in Five-Year Plan Evaluation, as needed - Post link to public view of SPR if available |
| OCT | - Continue entering SPR data - Process remaining grant reimbursements | - Process reimbursement requests - Prepare RFA/travel request for Jan. monitoring visits - Monitor incoming Conference Scholarship applications, log - Quarterly Project Status Reports due; send reminder & collect; notify LSTA Consultant of issues. | - Manage registration and logistics for webinars/workshops as needed - Prepare any webinar/workshop materials as needed | - Participate in Five-Year Plan Evaluation, as needed |
| NOV | - Continue entering SPR data | - Process reimbursement requests - Monitor incoming Conference Scholarship applications, log | - Log all LOIs, NC Cardinal apps as received - Prepare spreadsheet of all LOIs, NC Cardinal apps received |  |
| DEC | - LSTA State Program Report (SPR) is due to IMLS on Dec 30 | - Assist with summary of financial information for interim FSR if needed - Process reimbursement requests - Monitor incoming Conference Scholarship applications, log - Agreements for Conference Scholarships | - Prepare merge for LOI responses - Send LOI responses |  |
| JAN |  | - Process reimbursement requests - Monitor grantees spending status, notify LSTA Consultant of awards w/no expenditures after Jan. 15 if needed after reviewing Project Status Reports - Monitor incoming Conference Scholarship applications, log - Mid-Year and Q2 Project Status Reports due; send reminder & collect; notify LSTA Consultant of issues. - Process reimbursements related to monitoring visits |  | - Conduct Annual Equipment Tracking Survey |
| FEB |  | - Process reimbursement requests - Monitor incoming Conference Scholarship applications, log | - Log all grant applications as received; review for major data (signatures, agreement of top page with budget totals, match, IDC) - Export Formsite data; Prepare spreadsheet of all applications received |  |
| MAR |  | - Process reimbursement requests - Monitor incoming Conference Scholarship applications, log - Conference Scholarship agreements | - Prepare RFA for Advisory Committee meeting |  |
| APRIL |  | - Process reimbursement requests - Monitor grantees spending status, notify LSTA Consultant of awards w/no expenditures after Apr. 15 - Review/update online Final Report Form - Monitor incoming Conference Scholarship applications, log - Q3 Project Status Reports due; send reminder & collect; notify LSTA Consultant of issues. | - Shift files to make room for new year’s files in Program Assistant office as needed - Prepare letters and certificates for outgoing Advisory Committee members |  |
| MAY |  | - Request verification of federal expenditure cut-off date – from Budget Office - Post final report print view - Send final report link to grantees with completed projects - Monitor grantees spending status - Process reimbursement requests - Send email to notify grantees of mid-June federal expenditure cut-off with 3-day buffer - Monitor incoming Conference Scholarship applications, log | - Prepare handouts, name tents, packets, letters/certificates for Advisory Committee meeting; arrange catering - Process Advisory Committee reimbursements - Prepare merges to notify funded and not funded applicants in consultation with Federal Programs Consultant - Prepare web page updates for grant awards - Prepare grant agreement log/tracking log spreadsheet for new awards |  |
| JUNE AND JULY |  | - Process reimbursements by mid-June federal expenditure cut-off - Continue sending final report link to completed projects - Monitor incoming Conference Scholarship applications, log - Conference Scholarship Agreements July 1 | - Post web page update for grant awards - Post library and DNCR media release - Prepare merge/bulk file for grant agreements - Send grant agreement package with supplemental documents - Update Executed Agreement memo - Post updated reimbursement and budget revision info to web page - Update LSTA Cumulative Applications spreadsheet on K - Set up paperless filing system for new grants |  |