## Sheet1
TASKS | ASSIGNED TO | DUE DATE | ü | COMMENTS
AUCTION DETAILS
Determine volunteer needs; more needed for registration | Cassie/Rebecca | 2016-01-30 | ü
Early volunteer training | Leigh Ann, Mary Beth
3-4 check in full service check-in stations with use of large, easily readable directional signage | Leigh Ann, Mary Beth |  | ü | Note: attendees should be able to purchase additional beverages at the bar.
Gather quarter containers for tables | Mary Beth | 2016-02-01 |  | Mary Beth - Mason jars
Create handout that explains Piccadilly Auction | Cassie | 2016-02-01
Count auction paddles, tokens, etc. | Cassie / Leigh Ann | 2016-01-20 | ü | Leigh Ann
Create additional paddles, tokens if needed | Leigh Ann | 2016-02-05 | ü | Leigh Ann
Determine pricing for live and silent auction | Cassie/Rebecca | 2016-02-05
Prepare silent auction bid sheets | Cassie/Rebecca | 2016-02-08
Pick up wine and beer | Committee | Various |  | Continually; beer on day of event
AWARDS
Solicit award nominations | Cassie | 2016-01-15 | ü | Dec. 29, Jan. 5
Select Business of the Year | Recommendations to board | 2016-01-22 | ü
Design Awards | Design Committee | 2016-01-22 | ü | Jan. 19
Volunteer of the Year | Org Committee | 2016-01-22 | ü | Zack Geary
Manager's Award | Cassie | 2016-01-22 | ü | Zero Waste
Plaque information to Tona | Cassie | 2016-01-25 | ü
Personal invitations to winner | Cassie | 2016-01-22 | ü
Determine award presenters | Org Committee | 2016-01-29 | ü
BOARD
Design board ballot | Cassie/Rebecca | 2016-01-05 | ü | Confirming ballot
Advertise board openings in newsletter | Cassie |  | ü | Board solicitied
Establish board slate | Exec Committee | N/A | ü | Board solicitied
CATERING
Request catering bids from members | Cassie | 2015-12-18 | ü | Bids due Jan. 8; sent to CP, HF, La Rambla, Barberry, Pura Vida, BP (reminder sent Dec. 30)
Select caterer | Committee | 2015-01-08 | ü | Golden Valley
Confirm count with caterer | Cassie/Rebecca | 2016-02-08
DONATIONS
Email soliciting auction donations | Cassie | 2016-01-04 | ü | Ongoing
Create donation tracker spread sheet | Cassie | 2015-12-08 | ü
Wine and beer solicitations | Committee | Ongoing |  | Ongoing
Solicit auction items | Committee | Ongoing |  | Ongoing
LOGISTICS
Select date | Committee | 2015-10-01 | ü | Feb. 11, 2016
Reserve location | Cassie | 2015-10-01 | ü | Grand Ballroom
Lots of MDA bling around the room | Rebecca / Leslie | Day of
No centerpieces - decorate around quarter jars | Cassie/Rebecca | 2016-02-08
Pack: Guest list, starting cash, iPads, quarters | Cassie/Rebecca | 2016-02-11
Pick up quarters at First Fed (more than last year) | Cassie/Rebecca | 2016-02-11
Schlep stuff back to the office | Volunteers | 2016-02-11
Invoice guests | Cassie | 2016-02-15
Mailing
Design dinner invitation | Cassie/Rebecca | 2016-01-05 | ü | Mailed Jan. 13
Create mailing labels for all members, officials | Cassie | 2016-01-05 | ü | Jan. 13
Mail invitation and confirming ballot | Cassie/Rebecca | 2016-01-11 | ü | Jan. 13
Thank you cards to donors | Cassie | 2016-02-19
PROGRAM
Gather committee reports | Cassie | 2016-02-01
Write script | Cassie | 2016-02-05
Send script to speakers | Cassie | 2016-02-05
Create slide show program | Cassie/Rebecca | 2016-02-08
Create written program, schedule, auction items and pricing, committee reports | Cassie/Rebecca | 2016-02-08
| 2015 Winners |  |  | Presenter(s)
1 - Volunteer of the Year | Zack Geary |  |  | Rebecca
2 - Outstanding Window Display | Poseyland |  |  | Jenny Berg
3 - Downtown Beautification | McMinnville Garden Club |  |  | Zack Geary
4 - Outstanding New Signage | Ransom Spirits |  |  | Maria Stuart
5 - Outstanding Associate Member | Pacific Frame |  |  | Sylla McClellan
6 - Outstanding Exterior Renovation | Wild Haven Property Management
7 - Outstanding Interior Renovation | AmeriTitle
8 - Outstanding New construction | KAOS Building |  |  | Debbie Harmon Ferry
9 - Manager's Award | Zero Waste |  |  | Cassie
10 - Business of the Year | The Bitter Monk |  |  | Scott Cunningham